## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
1 | Game | Player | As a user, I can register the game | I can easily login to the game |  |  | 1 | TODO
2 | Simulator | Player | The application provides a message to user 'your bank account is created' | I have an idea for my bank account |  |  | 1 | TODO
3 | Simulator | Player | After create bank account it will add Rs.1000 | I know my amount |  |  | 1 | TODO
4 | Game | Player | Then to log in to the game | I can enter the game main menu |  |  | 1 | TODO
5 | Game | Player | As a user, see the game main menu, it shows all the scenarios in the menu(About, Leadership Board, Portfolio, Market History) | I can navigate any screen in the main menu |  |  | 1 | TODO
6 | Simulator | Player | If a minimum player count is 3 and it goes to 5 players. | can have an competition |  |  | 2 | TODO
7 | Simulator | Player | Definitely, only one human player is needeed to play the game. | I can play with another user or AI player |  |  | 2 | TODO
8 | Simulator | Player | If a user starts the game it shows a message 'Waiting for other players'. | I have to wait a few minutes for other players |  |  | 2 | TODO
9 | Simulator | Player | If before one minute, human players are joined more than 3 then AI players are not assigned | So we can play the game against humans rather than AI. |  |  | 3 | TODO
10 | Simulator | Player | If After one minute, two human players are joined to the game, it will start with two human players and only one AI player | I can have game experience with one real user and one AI user |  |  | 3 | TODO
11 | Simulator | Player | If before one minute, joined the 3 or above human players never provide AI users | I can play with real human players |  |  | 2 | TODO
12 | Simulator | Player | After all players are joined to the game 'game board' will display | so that its fair |  |  | 1 | TODO
13 | Simulator | Player | Gameboard should provide Rumours tab, Turns, buy/sell option, time of a turn, Current portfolio, bank balance | to make things interesting |  |  | 1 | TODO
14 | Simulator | Player | Affected stocks and events which have happened equipment etc. | to see what effects have taken place in the market |  |  | 1 | TODO
15 | Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. |  | 1 | TODO
16 | Simulator | Player | Know how many turns have passed since the start of the game | I know how far into the game I am |  |  | 1 | TODO
17 | Simulator | Player | See variation between the prices of shares in the market. | Share prices always change it does not have the same price. | This is the stock value model |  | 2 | TODO
18 | Game | Player | The player should be only able to buy shares according to his cash balance | so that it is fair |  |  | 3 | TODO
19 | Game | Player | Be able to see the current price of shares | they can decide what to buy/sell |  |  | 2 | TODO
20 | Game | Player | To get rumors whether to buy or sell shares. | I can make decisions whether buy or sell |  |  | 2 | TODO
21 | Game | Player | To get the details of what happened in the market. | I can take an idea about the market |  |  | 2 | TODO
22 | Game | Player | To get the time available for a specific turn. | so that it will make the the player take quick decisions |  |  | 1 | TODO
23 | Simulator | Player | Events should be fired according to sectors (eg:Technology,Health) | to make the game interesting and not the same |  |  | 3 | TODO
24 | Simulator | Player | A change in the stock price of each company at each game. | to make the stock prices vary which will make an interest among the players |  |  | 3 | TODO
25 | Game | Player | To be able to view the stock which I have bought previously and sold (Portfolio) | I can see historical data to get an overall understanding |  |  | 3 | TODO
26 | Game | Player | During the game, I should be able to see my portfolio | I can take an idea for future plans. |  |  | 4 | TODO
27 | Game | Player | At the end of each game to show my profit/loss | I can understand my weakness and performance |  |  | 4 | TODO
28 | Simulator | Player | All the events which are occurring now should be visible | to get an sight of the market |  |  | 3 | TODO
29 | Simulator | Player | At the end of each game winner should be displayed | to motivate the winner |  |  | 3 | TODO
30 | Simulator | Player | A player should be associated with a bank account and historical data should be stored. | that provide me withdraw and deposit. |  |  | 3 | TODO
31 | Simulator | Player | As a player, the Stock name is used as a unique identifier for each stock and player name is used as a unique identifier for each account | I can get easily infomation |  |  | 1 | TODO
32 | Game | Player | As a player, I can view the current price for each of the stocks specified stocks list. | to get decision to buy or sales the stocks. |  |  | 2 | TODO
33 | Game | Player | Variation of the companies stock market in previous games. | I can get easily information shair market. |  |  | 3 | TODO
34 | Simulator | Player | Historical data of stock related to companies | to get historical overview |  |  | 2 | TODO
35 | Game | Player | If user goes to winner list it shows his winning/lossing history only. | I can see how I play early games |  |  | 2 | TODO
36 | Game | Player | The user can view stocks, sector wise and there should be at least 3 stocks per sector and at least 4 sectors | I can get companies by sector wise. |  |  | 2 | TODO
37 | Simulator | Player | Events should be applying for a limited period of time. | so that it can affect the market in different ways in different games. |  |  | 2 | TODO
38 | Simulator | Player | AI player that implements some trading strategy that it uses to buy/sell stocks. | getting a challenge to me in the game. |  |  | 4 | TODO
39 | Simulator | Player | As a Player, I want to be able to buy shares so that I can make profit/loss. | so that I can move stock hear and there. |  |  | 1 | TODO

## Sprint 1
Sprint Goal: | Aiming for a D grade
Start Date: | 2018-05-28
End Date: | 2018-06-03
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to register the game. so that I can play the game. | 1 | T1.1 | Research how to create a user registration and how to handle sessions.
|  | T1.2 | Design a user Registration page | 5 | 4 | 2 | 2
|  | T1.3 | Create Test Cases | 1 | 1 | [5 empty] | 1
|  | T1.4 | Implement the Service
As a Player, I should get an message saying "Your account has been created" | 2 | T2.1 | Design a Service to expose this information | 2 | 2 | [5 empty] | 2
|  | T2.2 | Create Test Cases | 1 | 1 | [5 empty] | 1
|  | T2.3 | Design the UI | 2 | 2 |  | 2
As a Player, after registration we should be given Rs.1000 to start the game initially | 3 | T3.1 | Create the Services
|  | T3.2 | Create Test Cases
As a Player, I want to log in to the game. so that I can have previous history of the game saved. | 4 | T4.1 | Design the login page | 1 | 1 | 1
|  | T4.2 | Implement the Service | 5 | 4 | [6 empty] | 4
|  | T4.3 | Create Test Cases | 1 | 1 | [6 empty] | 1
As a Player, I see the game main menu, it shows all the scenarios in the menu(About, Leadership Board, Portfolio, Market History). so that I can navigate any screen in the main menu | 5 | T5.1 | Design the UI to show this information | 3 | 2 |  | 2
|  | T5.2 | Create Test Cases | 1 | 1 | [6 empty] | 1
As a Player, After all players are joined to the game 'gameboard' will be display. So that it is fair for all players | 12 | T12.1 | Design the UI | 2 | 2 |  |  | 2
|  | T12.2 | Handle the players
|  | T12.3 | Create Test Cases
As a Player, the Gameboard should provide Rumours tab, Turns, buy/sell option, time of a turn, Current portfolio, bank balance. so that to make things interesting | 13 | T13.1 | Research how to auto genarate Rumours | 2 | 1 | 1
|  | T13.2 | Create Tables for bank and buy/sell trascastions to track user activites.
|  | T13.3 | Create Test Cases
|  | T13.4 | Design the UI | 3 | 2 |  |  | 2
As a Player, I want to see the effected stocks and events which have happened. So that I can have an overall view of the market | 14 | T14.1 | Reasearch to create algorithm for stock events | 2 | 1 | 1
|  | T14.2 | UI to show this information | 2 | 3 |  |  |  |  | 3
|  | T14.3 | Create Test Cases
|  | T14.4 | Implementation of the service
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited turns for the whole game | 15 | T15.1 | Research on handling the time among several players.
|  | T15.2 | Design a solution for this game
|  | T15.3 | Create Test Cases
|  | T15.4 | Implement the solution | 4 | 5 |  |  | 2 | 3
As a Player, I want to how many turns have passed since the start of the game. so that I know how far into the game I have gone. | 16 | T16.1 | Storyboard a UI to show this information | 2 | 3 |  |  |  |  | 3
|  | T16.2 | Design a Service to expose this information | 3 | 4 | [5 empty] | 4
|  | T16.3 | Create Test Cases
As a Player, I want to be able to buy shares so that I can make profit/loss. | 39 | T39.1 | Design a Service to handle the incoming request | 1 | 1 | [6 empty] | 1
|  | T39.2 | Create Test Cases
|  | T39.3 | Implement the Service | 2 | 3 | [6 empty] | 3
|  | T39.4 | Implement the UI | 2 | 3 | [5 empty] | 3
|  | T39.5 | Connect the Service to the UI | 2 | 3 | [5 empty] | 3
As a Player, I want to get the time available for a specific turn. so that it will make the player can make quick decisions. | 24 | T24.1 | Implement the Service | 4 | 3 | [6 empty] | 3
|  |  | Sprint Countdown: | 53 | 53 | 5 | 6 | 6 | 3 | 6 | 14 | 13

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
T1.1 Research how to create a user login and how to handle sessions. |  | Taken to Sprint 2
T1.2 Design a user Registration page | Complete
T1.3 Create Test Cases | Complete
T1.4 Implement the Service |  | Taken to Sprint 2
T2.1 Design a Service to expose this information | Complete
T2.2 Create Test Cases | Complete
T2.3 Design the UI | Complete
T3.1 Create the Services |  | Taken to Sprint 2
T3.2 Create Test Cases |  | Taken to Sprint 2
T4.1 Design the login page | Complete
T4.2 Implement the Service | Complete
T4.3 Create Test Cases | Complete
T5.1 Design the UI to show this information | Complete
T5.2 Create Test Cases | Complete
T12.1 Design the UI | Complete
T12.2 Handle the players |  | Taken to Sprint 2
T12.3 Create Test Cases |  | Taken to Sprint 2
T13.1 Research how to auto genarate Rumours | Complete
T13.2 Create Tables for bank and buy/sell trascastions to track user activites. |  | Taken to Sprint 2
T13.3 Create Test Cases |  | Taken to Sprint 2
T13.4 Design the UI | Complete
T14.1 Reasearch to create algorithm for stock events | Complete
T14.2 UI to show this information | Complete
T14.3 Create Test Cases |  | Taken to Sprint 2
T14.4 Implementation of the service |  | Taken to Sprint 2
T15.1 Research on handling the time among several players. |  | Taken to Sprint 2
T15.2 Design a solution for this game |  | Taken to Sprint 2
T15.3 Create Test Cases |  | Taken to Sprint 2
T15.4 Implement the solution | Complete
T16.1 Storyboard a UI to show this information | Complete
T16.2 Design a Service to expose this information | Complete
T16.3 Create Test Cases |  | Taken to Sprint 2
T39.1 Design a Service to handle the incoming request | Complete
T39.2 Create Test Cases |  | Taken to Sprint 2
T39.3 Implement the Service | Complete
T39.4 Implement the UI | Complete
T39.5 Connect the Service to the UI | Complete
T24.1 Implement the Service | Complete

## Sprint 2
Sprint Goal: | Aiming for a C grade
Start Date: | 2018-06-04
End Date: | 2018-06-10
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Brought From Sprint 1
As a Player, I want to register the game. so that I can play the game. | 1 | T1.1 | Research how to create a user login and how to handle sessions.
|  | T1.4 | Implement the Service | 2 | 2 | [5 empty] | 2
As a Player, after registration we should be given Rs.1000 to start the game initially | 3 | T3.1 | Create the Services | 2 | 2 | [6 empty] | 2
|  | T3.2 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
As a Player, After all players are joined to the game 'gameboard' will be display. So that it is fair for all players | 12 | T12.3 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
|  | T12.2 | Handle the players
As a Player, the Gameboard should provide Rumours tab, Turns, buy/sell option, time of a turn, Current portfolio, bank balance. so that to make things interesting | 13 | T13.2 | Create Tables for bank and buy/sell trascastions to track user activites.
|  | T13.3 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
As a Player, I want to see the effected stocks and events which have happened. So that I can have an overall view of the market | 14 | T14.3 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
|  | T14.4 | Implementation of the service
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited turns for the whole game | 15 | T15.1 | Research on handling the time among several players.
|  | T15.2 | Design a solution for this game
|  | T15.3 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
As a Player, I want to how many turns have passed since the start of the game. so that I know how far into the game I have gone. | 16 | T16.3 | Create Test Cases | 1 | 0.5 | [5 empty] | 0.5
As a Player, I want to be able to buy shares so that I can make profit/loss. | 39 | T39.2 | Create Test Cases | 1 | 1 | [5 empty] | 1
Sprint 2
If a minimum player count is 3 and it goes to 5 players. So that we can have an competition. | 6 | T6.1 | Researching on how to handle multiple players
|  | T6.2 | Writing the Service accordingly
|  | T6.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
If only one human player is present to play the game. Then the others will be AI players. | 7 | T7.1 | Research on creating AI players | 1 | 1 | 1
|  | T7.2 | Implementing the AI player
|  | T7.3 | Implementing the service
|  | T7.4 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
If a user starts the game it shows a message 'Waiting for other players'. So it will allow him to wait for human players rather than AI players. | 8 | T8.1 | Check for human players availability
|  | T8.2 | Implementing the service
|  | T8.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
If before one minute, human players are joined more than 3 then AI players are not assigned. So that we can play against humans rather than AI players. | 11 | T11.1 | Handling the wait time between the players
|  | T11.2 | Implementing the service
|  | T11.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
See variation between the prices of shares in the market. So that the stock prices always changes it does not have the same price at each game. | 17 | T17.1 | Create method for receiving and showing stock value details
|  | T17.2 | Create stock value changing algorithms
|  | T17.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
Be able to see the current price of shares. So that player can make decisions on what to buy/sell | 19 | T19.1 | Implementing the algorithm to generate the stock changing
|  | T19.2 | Display the server response in UI
|  | T19.3 | Create a test case to test the algorithm | 1 | 0.5 | [6 empty] | 0.5
To get rumors whether to buy or sell shares. Using the hints I can guess on what to buy/sell. | 20 | T20.1 | Implementing the algorithm to generate the rumours
|  | T20.2 | Handling the responses from the server
|  | T20.3 | Create a test case to test the algorithm | 1 | 0.5 | [6 empty] | 0.5
To get the details of what happened in the market. I can get an idea about the current market | 21 | T21.1 | Connecting the service to the UI
As a player, I can view the current price for each of the stocks specified stocks list. To make an decision to buy or sales the stocks. | 32 | T32.1 | Implementation of the buying method
|  | T32.2 | Implementation of the sell method
|  | T32.3 | Create a test case | 1 | 0.5 | [6 empty] | 0.5
Historical data of stock related to companies. So that the players can get a historical overview | 34 | T34.1 | Implementing method for retrieve historical data from DB | 1 | 2 | [5 empty] | 2
|  | T34.2 | Implementing method for show retrieved data in client side | 1 | 2 | [6 empty] | 2
|  | T34.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
If user goes to winner list it shows his winning/lossing history only. I can see how I played the early games in which I participated | 35 | T35.1 | Implementing a method to save all user data | 2 | 3 | 3
|  | T35.2 | Implementing a method to show all the data in the client side | 2 | 3 | [6 empty] | 3
|  | T35.3 | Create Test Cases | 1 | 0.5 | [6 empty] | 0.5
The user can view stocks, sector wise and there should be at least 3 stocks per sector and at least 4 sectors. I can get companies by sector wise. | 36 | T36.1 | Implementing a filtering method to show the sectors of companies
Events should be applying for a limited period of time. So that it can effect the market in different ways in different games. | 37 | T37.1 | Implementing the probability funtion for the events
|  | T37.2 | Create Test Cases | 1 | 1 | [6 empty] | 1
|  |  | Sprint Countdown: | 29 | 25 | 4 | 0 | 0 | 0 | 0 | 8 | 13

## Sprint 2 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
T1.1 Research how to create a user login and how to handle sessions. |  | Taken to Sprint 3
T1.4 Implement the Service | Complete
T3.1 Create the Services | Complete
T3.2 Create Test Cases | Complete
T12.3 Create Test Cases | Complete
T12.2 Handle the players |  | Taken to Sprint 3
T13.2 Create Tables for bank and buy/sell trascastions to track user activites. |  | Taken to Sprint 3
T13.3 Create Test Cases | Complete
T14.3 Create Test Cases | Complete
T14.4 Implementation of the service |  | Taken to Sprint 3
T15.1 Research on handling the time among several players. |  | Taken to Sprint 3
T15.2 Design a solution for this game |  | Taken to Sprint 3
T15.3 Create Test Cases | Complete
T16.3 Create Test Cases | Complete
T39.2 Create Test Cases | Complete
T6.1 Researching on how to handle multiple players |  | Taken to Sprint 3
T6.2 Writing the Service accordingly |  | Taken to Sprint 3
T6.3 Create Test Cases | Complete
T7.1 Research on creating AI players | Complete
T7.2 Implementing the AI player |  | Taken to Sprint 3
T7.3 Implementing the service |  | Taken to Sprint 3
T7.4 Create Test Cases | Complete
T8.1 Check for human players availability |  | Taken to Sprint 3
T8.2 Implementing the service |  | Taken to Sprint 3
T8.3 Create Test Cases | Complete
T11.1 Handling the wait time between the players |  | Taken to Sprint 3
T11.2 Implementing the service |  | Taken to Sprint 3
T11.3 Create Test Cases | Complete
T17.1 Create method for receiving and showing stock value details |  | Taken to Sprint 3
T17.2 Create stock value changing algorithms |  | Taken to Sprint 3
T17.3 Create Test Cases | Complete
T19.1 Implementing the algorithm to generate the stock changing |  | Taken to Sprint 3
T19.2 Display the server response in UI |  | Taken to Sprint 3
T19.3 Create a test case to test the algorithm | Complete
T20.1 Implementing the algorithm to generate the rumours |  | Taken to Sprint 3
T20.2 Handling the responses from the server |  | Taken to Sprint 3
T20.3 Create a test case to test the algorithm | Complete
T21.1 Connecting the service to the UI |  | Taken to Sprint 3
T32.1 Implementation of the buying method |  | Taken to Sprint 3
T32.2 Implementation of the sell method |  | Taken to Sprint 3
T32.3 Create a test case | Complete
T34.1 Implementing method for retrieve historical data from DB | Complete
T34.2 Implementing method for show retrieved data in client side | Complete
T34.3 Create Test Cases | Complete
T35.1 Implementing a method to save all user data | Complete
T35.2 Implementing a method to show all the data in the client side | Complete
T35.3 Create Test Cases | Complete
T36.1 Implementing a filtering method to show the sectors of companies |  | Taken to Sprint 3
T37.1 Implementing the probability funtion for the events |  | Taken to Sprint 3
T37.2 Create Test Cases | Complete

## Sprint 3
Sprint Goal: | Aiming for a B grade
Start Date: | 2018-06-11
End Date: | 2018-06-17
User Story | PBL ID# |  | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Brought From Sprint 2
As a Player, I want to register the game. so that I can play the game. | 1 | T1.1 | Research how to create a user login and how to handle sessions. | 1 | 1 | 1
As a Player, After all players are joined to the game 'gameboard' will be display. So that it is fair for all players | 12 | T12.2 | Handle the players
As a Player, the Gameboard should provide Rumours tab, Turns, buy/sell option, time of a turn, Current portfolio, bank balance. so that to make things interesting | 13 | T13.2 | Create Tables for bank and buy/sell trascastions to track user activites. | 4 | 5 | [5 empty] | 2 | 3
As a Player, I want to see the effected stocks and events which have happened. So that I can have an overall view of the market | 14 | T14.4 | Implementation of the service
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited turns for the whole game | 15 | T15.1 | Research on handling the time among several players. | 1 | 2 | 2
|  | T15.2 | Design a solution for this game
If a minimum player count is 3 and it goes to 5 players. So that we can have an competition. | 6 | T6.1 | Researching on how to handle multiple players | 1 | 1 |  | 1
|  | T6.2 | Writing the Service accordingly
If only one human player is present to play the game. Then the others will be AI players. | 7 | T7.2 | Implementing the AI player
|  | T7.3 | Implementing the service
|  | T7.4 | Create Test Cases | 0.5 | 0.5 | [5 empty] | 0.5
If a user starts the game it shows a message 'Waiting for other players'. So it will allow him to wait for human players rather than AI players. | 8 | T8.1 | Check for human players availability
|  | T8.2 | Implementing the service
|  | T8.3 | Create Test Cases | 0.5 | 0.5 | [5 empty] | 0.5
If before one minute, human players are joined more than 3 then AI players are not assigned. So that we can play against humans rather than AI players. | 11 | T11.1 | Handling the wait time between the players
|  | T11.2 | Implementing the service
|  | T11.3 | Create Test Cases | 0.5 | 0.5 | [5 empty] | 0.5
See variation between the prices of shares in the market. So that the stock prices always changes it does not have the same price at each game. | 17 | T17.1 | Create method for receiving and showing stock value details | 2 | 3 | [5 empty] | 3
|  | T17.2 | Create stock value changing algorithms | 5 | 6 |  |  |  | 3 | 3
Be able to see the current price of shares. So that player can make decisions on what to buy/sell | 19 | T19.1 | Implementing the algorithm to generate the stock changing
|  | T19.2 | Display the server response in UI
To get rumors whether to buy or sell shares. Using the hints I can guess on what to buy/sell. | 20 | T20.1 | Implementing the algorithm to generate the rumours | 5 | 7 |  |  |  |  | 1 | 2 | 4
|  | T20.2 | Handling the responses from the server | 5 | 6 |  |  |  | 2 | 2 | 2
To get the details of what happened in the market. I can get an idea about the current market | 21 | T21.1 | Connecting the service to the UI
As a player, I can view the current price for each of the stocks specified stocks list. To make an decision to buy or sales the stocks. | 32 | T32.1 | Implementation of the buying method
|  | T32.2 | Implementation of the sell method
The user can view stocks, sector wise and there should be at least 3 stocks per sector and at least 4 sectors. I can get companies by sector wise. | 36 | T36.1 | Implementing a filtering method to show the sectors of companies
Events should be applying for a limited period of time. So that it can effect the market in different ways in different games. | 37 | T37.1 | Implementing the probability funtion for the events | 4 | 4 |  | 2 | 2
| 37 | T37.2 | Create Test Cases
Sprint 3
If before one minute, human players are joined more than 3 then AI players are not assigned | 9 | T9.1 | Create the Services
|  | T9.2 | Create Test Case | 0.5 | 0.5 | [5 empty] | 0.5
If After one minute, two human players are joined to the game, it will start with two human players and only one AI player | 10 | T10.1 | Create the Services
|  | T10.2 | Create Test Case | 2 | 1 | [5 empty] | 1
The player should be only able to buy shares according to his cash balance | 18 | T18.1 | Apply validation during the game
|  | T18.2 | Create Test Cases
Events should be fired according to sectors (eg:Technology,Health, etc) | 23 | T23.1 | Display Sectors in UI | 2 | 3 | 3
A change in the stock price of each company at each game. | 24 | T24.1 | Create method for store stock value in the database | 3 | 5 | 1 | 2 | 2
To be able to view the stock which I have bought previously and sold (Portfolio) | 25 | T25.1 | Retrive historical data of comapany stock from database | 3 | 4 |  |  |  |  | 1 | 1 | 2
|  | T25.2 | Send above data to client and dispaly it | 3 | 4 | [5 empty] | 1 | 3
|  | T25.3 | Create Test Cases
All the events which are occurring now should be visible | 28 | T28.1 | Events should be shown to the user in the news feed tab | 2 | 3 | [5 empty] | 3
At the end of each game winner should be displayed | 29 | T29.1 | Show a Popup message to the winner
|  | T29.2 | Create Test Cases
A player should be associated with a bank account and historical data should be stored. | 30 | T30.1 | Create Bank Account instances for each player
|  | T30.2 | Store data to DB tables
Variation of the companies stock market in previous games. | 33 | T33.1 | Store historical data to DB
|  | T33.2 | Update portfolio accordingly
|  |  | Sprint Countdown: | 45 | 57 | 7 | 5 | 4 | 5 | 7 | 17 | 12

## Sprint 3 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
T1.1 Research how to create a user login and how to handle sessions. | Complete
T12.2 Handle the players |  | Taken to Sprint 4
T13.2 Create Tables for bank and buy/sell trascastions to track user activites. | Complete
T14.4 Implementation of the service | Complete
T15.1 Research on handling the time among several players. | Complete
T15.2 Design a solution for this game |  | Taken to Sprint 4
T6.1 Researching on how to handle multiple players | Complete
T6.2 Writing the Service accordingly |  | Taken to Sprint 4
T7.2 Implementing the AI player |  | Taken to Sprint 4
T7.3 Implementing the service |  | Taken to Sprint 4
T7.4 Create Test Cases | Complete
T8.1 Check for human players availability |  | Taken to Sprint 4
T8.2 Implementing the service |  | Taken to Sprint 4
T8.3 Create Test Cases | Complete
T11.1 Handling the wait time between the players |  | Taken to Sprint 4
T11.2 Implementing the service |  | Taken to Sprint 4
T11.3 Create Test Cases | Complete
T17.1 Create method for receiving and showing stock value details | Complete
T17.2 Create stock value changing algorithms | Complete
T19.1 Implementing the algorithm to generate the stock changing |  | Taken to Sprint 4
T19.2 Display the server response in UI |  | Taken to Sprint 4
T20.1 Implementing the algorithm to generate the rumours | Complete
T20.2 Handling the responses from the server | Complete
T21.1 Connecting the service to the UI |  | Taken to Sprint 4
T32.1 Implementation of the buying method |  | Taken to Sprint 4
T32.2 Implementation of the sell method |  | Taken to Sprint 4
T36.1 Implementing a filtering method to show the sectors of companies |  | Taken to Sprint 4
T37.1 Implementing the probability funtion for the events | Complete
T37.2 Create Test Cases |  | Taken to Sprint 4
T9.1 Create the Services |  | Taken to Sprint 4
T9.2 Create Test Case | Complete
T10.1 Create the Services |  | Taken to Sprint 4
T10.2 Create Test Case | Complete
T18.1 Apply validation during the game |  | Taken to Sprint 4
T18.2 Create Test Cases |  | Taken to Sprint 4
T23.1 Display Sectors in UI | Complete
T24.1 Create method for store stock value in the database | Complete
T25.1 Retrive historical data of comapany stock from database | Complete
T25.2 Send above data to client and dispaly it | Complete
T25.3 Create Test Cases |  | Taken to Sprint 4
T28.1 Events should be shown to the user in the news feed tab | Complete
T29.1 Show a Popup message to the winner |  | Taken to Sprint 4
T29.2 Create Test Cases |  | Taken to Sprint 4
T30.1 Create Bank Account instances for each player |  | Taken to Sprint 4
T30.2 Store data to DB tables |  | Taken to Sprint 4
T33.1 Store historical data to DB |  | Taken to Sprint 4
T33.2 Update portfolio accordingly |  | Taken to Sprint 4

## Sprint 4
Aiming for a A grade
Start Date: | 2018-06-18
End Date: | 2018-06-26
User Story | PBL ID# |  | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
Brought From Sprint 3
As a Player, After all players are joined to the game 'gameboard' will be display. So that it is fair for all players | 12 | T12.2 | Handle the players | 4 | 8 | 1 | 2 | 1 | 1 | 2 | 1
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited turns for the whole game | 15 | T15.2 | Design a solution for this game | 3 | 5 | Day 5: 1; Day 6: 2; Day 7: 1; Day 8: 1
If a minimum player count is 3 and it goes to 5 players. So that we can have an competition. | 6 | T6.2 | Writing the Service accordingly | 3 | 3 | Day 6: 1; Day 7: 2
If only one human player is present to play the game. Then the others will be AI players. | 7 | T7.2 | Implementing the AI player | 5 | 8 | Day 1: 1; Day 2: 1; Day 4: 1; Day 5: 1; Day 6: 4
|  | T7.3 | Implementing the service | 3 | 3 | Day 6: 3
If a user starts the game it shows a message 'Waiting for other players'. So it will allow him to wait for human players rather than AI players. | 8 | T8.1 | Check for human players availability | 3 | 2 | Day 7: 2
|  | T8.2 | Implementing the service | 3 | 2 | bar: Day 7 to Day 8
If before one minute, human players are joined more than 3 then AI players are not assigned. So that we can play against humans rather than AI players. | 11 | T11.1 | Handling the wait time between the players | 4 | 6 | Day 9: 6
|  | T11.2 | Implementing the service | 4 | 5 | Day 9: 5
Be able to see the current price of shares. So that player can make decisions on what to buy/sell | 19 | T19.1 | Implementing the algorithm to generate the stock changing | 4 | 6 | Day 3: 1; Day 4: 2; Day 5: 2; Day 6: 1
|  | T19.2 | Display the server response in UI | 2 | 2 | bar: Day 1 to Day 2
To get the details of what happened in the market. I can get an idea about the current market | 21 | T21.1 | Connecting the service to the UI | 2 | 3 | Day 1: 2; Day 2: 1
As a player, I can view the current price for each of the stocks specified stocks list. To make an decision to buy or sales the stocks. | 32 | T32.1 | Implementation of the buying method | 2 | 4 | Day 4: 2; Day 5: 2
|  | T32.2 | Implementation of the sell method | 2 | 3 | Day 1: 2; Day 2: 1
The user can view stocks, sector wise and there should be at least 3 stocks per sector and at least 4 sectors. I can get companies by sector wise. | 36 | T36.1 | Implementing a filtering method to show the sectors of companies | 2 | 2 | Day 6: 2
Events should be applying for a limited period of time. So that it can effect the market in different ways in different games. | 37 | T37.2 | Create Test Cases | 0.5 | 0.5 | Day 7: 0.5
If before one minute, human players are joined more than 3 then AI players are not assigned | 9 | T9.1 | Create the Services | 4 | 5 | Day 7: 1; Day 8: 3; Day 9: 2
If After one minute, two human players are joined to the game, it will start with two human players and only one AI player | 10 | T10.1 | Create the Services | 4 | 4 | Day 8: 2; Day 9: 2
The player should be only able to buy shares according to his cash balance | 18 | T18.1 | Apply validation during the game | 4 | 6 | Day 7: 3; Day 8: 2; Day 9: 1
|  | T18.2 | Create Test Cases | 0.5 | 0.5 | Day 7: 0.5
To be able to view the stock which I have bought previously and sold (Portfolio) | 25 | T25.3 | Create Test Cases | 0.5 | 0.5 | Day 7: 0.5
At the end of each game winner should be displayed | 29 | T29.1 | Show a Popup message to the winner | 0.3 |  | Day 9: 0.3
|  | T29.2 | Create Test Cases | 1 | 0.5 | Day 7: 0.5
A player should be associated with a bank account and historical data should be stored. | 30 | T30.1 | Create Bank Account instances for each player | 3 | 5 | Day 1: 1; Day 2: 2; Day 3: 3
|  | T30.2 | Store data to DB tables | 3 | 3 | Day 6: 3
Variation of the companies stock market in previous games. | 33 | T33.1 | Store historical data to DB | 3 | 3 | Day 7: 3
|  | T33.2 | Update market history accordingly | 2 | 4 | Day 7: 2; Day 8: 2; Day 9: 1
Sprint 4
During the game, I should be able to see my portfolio | 26 | T26.1 | Implementing the service using SSE to send the updates | 5 | 6 | Day 6: 2; Day 7: 2; Day 8: 1; Day 9: 1
|  | T26.2 | Create Test Case | 0.5 | 0.5 | Day 7: 0.5
At the end of each game to show my profit/loss | 27 | T27.1 | Show a Popup message to the profit/loss | 1 | 1 | bar: Day 9
|  | T27.2 | Create Test Case | 0.5 | 0.5 | Day 7: 0.5
AI player that implements some trading strategy that it uses to buy/sell stocks. | 38 | T38.1 | Implementing AI players who are inteligent to adopt to situations | 5 | 9 |  |  | 1 | 1 | 1 | 2 | 2 | 2
|  | T38.2 | Create Test Case | 0.5 | 1 | bar: Day 7
|  |  | Sprint Countdown: | 84.3 | 112 | 8 | 8 | 6 | 7 | 9 | 21 | 23 | 14 | 19.3

## Sprint 4 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
T12.2 Handle the players | Complete
T15.2 Design a solution for this game | Complete
T6.2 Writing the Service accordingly | Complete
T7.2 Implementing the AI player | Complete
T7.3 Implementing the service | Complete
T8.1 Check for human players availability | Complete
T8.2 Implementing the service | Complete
T11.1 Handling the wait time between the players | Complete
T11.2 Implementing the service | Complete
T19.1 Implementing the algorithm to generate the stock changing | Complete
T19.2 Display the server response in UI | Complete
T21.1 Connecting the service to the UI | Complete
T32.1 Implementation of the buying method | Complete
T32.2 Implementation of the sell method | Complete
T36.1 Implementing a filtering method to show the sectors of companies | Complete
T37.2 Create Test Cases | Complete
T9.1 Create the Services | Complete
T10.1 Create the Services | Complete
T18.1 Apply validation during the game | Complete
T18.2 Create Test Cases | Complete
T25.3 Create Test Cases | Complete
T29.1 Show a Popup message to the winner | Complete
T29.2 Create Test Cases | Complete
T30.1 Create Bank Account instances for each player | Complete
T30.2 Store data to DB tables | Complete
T33.1 Store historical data to DB | Complete
T33.2 Update portfolio accordingly | Complete
T26.1 Implementing the service using SSE to send the updates | Complete
T26.2 Create Test Case | Complete
T27.1 Show a Popup message to the profit/loss | Complete
T27.2 Create Test Case | Complete
T38.1 Implementing AI players who are inteligent to adopt to situations | Complete
T38.2 Create Test Case | Complete